## JiraIDs
JiraID | Priority | Original Estimated dev time | Estimated test time | Dev Assigned to | Test Assigned to | Current Estimated dev time | Remaining dev time | Remaining dev time accumulated | Remain test time | Row of assigned dev | Row of assigned tester | DevLookup1 | Number of hours | Dev finishes | Testing starts | Column on Calendarwith Testing starts | Column on this sheet with testing starts | TestLookup1 | TestLookup2 | Test end date
MAR01 | 1 | 20 | 7 | Dev1 | Tester | 1 | 8 | 8 |  | 13 | 4 | 2 | 2 | 2019-02-18 | 2019-02-18 | G | AB | 0 | G | 2019-02-18 | Running total from Testing starts | 0 | 10 | 15 | 21 | 25 | 29 | 38 | 44
Formulas:
Testing starts = [Dev finishes]
Test end date = INDIRECT("Calendar!"&[TestLookup2]&"1")

## Calendar
 | time axis 2019-02-11 to 2019-04-27
Dev1 | 6 | 5 | 6 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Dev2 | 2019-02-11: 6; 2019-02-12: 6; 2019-02-13: 6; 2019-02-14: 6; 2019-02-19: 6; 2019-02-20: 6; 2019-02-21: 6; 2019-02-25: 6; 2019-02-27: 6
Tester | 2019-02-11: 4; 2019-02-12: 4; 2019-02-13: 6; 2019-02-14: 6; 2019-02-15: 6; 2019-02-18: 10; 2019-02-19: 5; 2019-02-20: 6; 2019-02-21: 4; 2019-02-22: 4; 2019-02-25: 3; 2019-02-26: 6; 2019-02-27: 6; 2019-02-28: 6
Tester2 | 2019-02-11: 3; 2019-02-12: 3; 2019-02-13: 3; 2019-02-14: 3; 2019-02-15: 3; 2019-02-18: 3; 2019-02-19: 3; 2019-02-20: 3; 2019-02-21: 3; 2019-02-22: 3; 2019-02-25: 3; 2019-02-26: 3; 2019-02-27: 3; 2019-02-28: 3; 2019-03-03: 3
Today | 2019-02-11: 2019-02-15
Column number with today in | 2019-02-11: 6; 2019-02-12: F
Cell with today's date in | bar: 2019-02-11
Dev1 running total from today | 2019-02-11: 0; 2019-02-12: 6; 2019-02-13: 12; 2019-02-14: 18; 2019-02-15: 24; 2019-02-18: 30; 2019-02-19: 36; 2019-02-20: 42
Dev2 running total from today | 2019-02-11: 0; 2019-02-12: 0; 2019-02-13: 0; 2019-02-14: 6; 2019-02-15: 12; 2019-02-18: 18; 2019-02-19: 18; 2019-02-20: 24

## Sheet5
I want to sum between two cells. The first cell is the current row plus the column that holds the current date. The second cell is the
4
7 | 5 | 3 | 4
2
OrderID
0
6
10
11
13
14

## Notes
Resource tracker
A Jira item enters the resource tracker once it has come of analysis and is ready for development. That is when it will get an estimated time, in hours