## Process
Requirement identified by end-user, someone in business, me (non-functional)
Coud be a bug, new feature, new integration, non-functional
If it is a bug then gets prioritised in term of severity
Whoever raised requirement talks to product owner. Product Owner asertains if reasonable requirements, is achivable, Diamond should be delivering it. I might be involved in this initial conversation
If genuine requirement then I will t-shirt size it and goes into the backlog. With an initial MOSCOW priority.
Periodic prioritisation session. Didn't follow sprints, may be triggered by someone in the business escalating an item or when we plan to complete work soon and need more.
Items that are high priority will get assigned to a sprint. This will be for analysis initially.
Once an item is ready for analysis, the BA, end-user and me will define requirements. Use-cases will be defined. The end-product of this analysis is a series of user stories. A user story will represent a piece of functionality in the format of As A... I want... So I can... This will include any business rules required to implement the requirement. We will identify what dependencies there is between user stories and if they all need to be released at once or incrementally.
Creation of technical specification. This will be part of the user story or additional document. I will also define what test data needs to be created to test it.
Once the technical definition has been written, I will brief in to developers and testers and get an actual estimation of actual development and test time in hours. Jira will be updated in terms of actual work items
Then it is ready to be assigned to a sprint for actual development.

## Enhanced consolidation
User identifies problem that data is being over-consolidated eg people who are different being considered the same
User goes to product owner. They do some analysis to identify if issue is real or not.
Talk to me and data analyst about possible solution
Data analyst creates document defining solution at high level
I give an initial t-shirt size. In this case X-Large
Goes into the backlog in Jira with X-Large and whatever priority it is give.