## JiraIDs
JiraID | Priority | Original Estimated dev time | Estimated test time | Dev Assigned to | Test Assigned to | Current Estimated dev time | Dev time so far used | Remaining dev time | Remaining dev time accumulated | Remain test time | Row of assigned dev | Row of assigned tester | DevLookup1 | Devlookup2 | Dev finishes | Testing starts | Column with Testing starts | TestLookup1
MAR01 | 1 | 20 | 5 | Dev1 | Tester | 30 |  | 20 | 20 | 5 | 3 | 9 | 5 | J | 2019-02-19 | 2019-02-19 | J
MAR02 | 2 | 26 | 5 | Dev1 | Tester2 |  |  | 10 | 30 | 3 | 3 | 11 | 8 | M | 2019-02-22 | 2019-02-22 | BU
MAR03 | 1 |  | 5 | Dev2 | Tester |  |  | 20 | 20 | 5 | 5 | 9 | 9 | N | 2019-02-25 | 2019-02-25 | BU
Formulas:
Dev finishes = INDIRECT("Calendar!"&[Devlookup2]&"1")
Testing starts = [Dev finishes]
Note on N1: Get the column which the remaining dev falls just below

## Calendar
 | time axis 2019-02-11 to 2019-04-27
Dev1 | 6 | 5 | 6 | 6 | 6 |  |  | 6 | 6 | 6 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Dev1 running total from today | 23 | 17 | 12 | 6 | 12 | 12 | 12 | 18 | 24 | 30 | 30 | 36 | 42 | 48 | 54 | 60 | 66 | 72 | 78 | 84 | 90 | 96 | 102 | 108 | 114 | 120 | 126 | 132 | 138 | 144 | 150 | 156 | 162 | 168 | 174 | 180 | 186 | 192 | 198 | 204 | 210 | 216 | 222 | 228 | 234 | 240 | 246 | 252 | 258 | 264 | 270 | 276 | 282 | 288 | 294 | 300 | 306 | 312 | 318 | 324 | 330 | 336 | 342 | 348 | 354 | 360 | 366 | 372 | 378 | 384 | 390 | 396
Dev2 | 2019-02-11: 6; 2019-02-12: 6; 2019-02-13: 6; 2019-02-14: 6; 2019-02-19: 6; 2019-02-20: 6; 2019-02-25: 6; 2019-02-27: 6
Dev2 running total from today | 2019-02-11: 24; 2019-02-12: 18; 2019-02-13: 12; 2019-02-14: 6; 2019-02-15: 6; 2019-02-16: 6; 2019-02-17: 6; 2019-02-18: 6; 2019-02-19: 12; 2019-02-20: 18; 2019-02-21: 18; 2019-02-22: 18; 2019-02-25: 24; 2019-02-26: 24; 2019-02-27: 30
Dev3 | 2019-02-11: 6; 2019-02-12: 6; 2019-02-13: 6; 2019-02-14: 6; 2019-02-15: 6; 2019-02-18: 6; 2019-02-19: 6; 2019-02-20: 6; 2019-02-21: 6; 2019-02-22: 3.5; 2019-02-25: 6; 2019-02-26: 6; 2019-02-27: 6; 2019-02-28: 6
Dev3 running total from today | 2019-02-11: 24; 2019-02-12: 18; 2019-02-13: 12; 2019-02-14: 6; 2019-02-15: 12; 2019-02-16: 12; 2019-02-17: 12; 2019-02-18: 18; 2019-02-19: 24; 2019-02-20: 30; 2019-02-21: 36; 2019-02-22: 39.5; 2019-02-25: 45.5; 2019-02-26: 51.5; 2019-02-27: 57.5; 2019-02-28: 63.5
Tester | 2019-02-11: 6; 2019-02-12: 6; 2019-02-13: 6; 2019-02-14: 6; 2019-02-15: 6; 2019-02-18: 6; 2019-02-19: 6; 2019-02-20: 6; 2019-02-21: 6; 2019-02-22: 6; 2019-02-25: 6; 2019-02-26: 6; 2019-02-27: 6; 2019-02-28: 6
Tester running total from today | 2019-02-11: 24; 2019-02-12: 18; 2019-02-13: 12; 2019-02-14: 6; 2019-02-15: 12; 2019-02-16: 12; 2019-02-17: 12; 2019-02-18: 18; 2019-02-19: 24; 2019-02-20: 30; 2019-02-21: 36; 2019-02-22: 42; 2019-02-25: 48; 2019-02-26: 54; 2019-02-27: 60; 2019-02-28: 66; 2019-03-03: 66
Tester2 | 2019-02-11: 3; 2019-02-12: 3; 2019-02-13: 3; 2019-02-14: 3; 2019-02-15: 3; 2019-02-16: 3; 2019-02-17: 3; 2019-02-18: 3; 2019-02-19: 3; 2019-02-20: 3; 2019-02-21: 3; 2019-02-22: 3; 2019-02-25: 3; 2019-02-26: 3; 2019-02-27: 3; 2019-02-28: 3; 2019-03-03: 3
Tester2 running total from today | 2019-02-11: 12; 2019-02-12: 9; 2019-02-13: 6; 2019-02-14: 3; 2019-02-15: 6; 2019-02-16: 9; 2019-02-17: 12
Today | 2019-02-11: 2019-02-14
Column number with today in | 2019-02-11: 5; 2019-02-12: E
Cell with today's date in | bar: 2019-02-11

## Sheet5
I want to sum between two cells. The first cell is the current row plus the column that holds the current date. The second cell is the

## Sheet6
Quantity Sold | Product | Salesperson | 20
5 | Apples | Tom
4 | Apples | Sarah
15 | Artichokes | Tom
3 | Artichokes | Sarah
22 | Bananas | Tom
12 | Bananas | Sarah
10 | Carrots | Tom
33 | Carrots | Sarah

## Notes
Resource tracker
A Jira item enters the resource tracker once it has come of analysis and is ready for development. That is when it will get an estimated time, in hours